## Instructions
Recruitment Strategy Tracker
The Recruitment Strategy Tracker tracks strategies and subject enrollment by month.
• This tracker should be updated on a monthly basis while the study is enrolling.
• The chart can be used to view enrollment progress by month.
Recruitment Activities Summary:
This table is a snapshot of your recruitment status.
• Actual # of Participants: This is a calculation. No need to input anything in these cells.
• Target # of Participants:
○ Pre-screened: Input the number of potential participants that you anticipate needing to prescreen in order to meet the enrollment goal
○ Screening: Input the number of potential participants that you anticipate needing to screen in order to meet the enrollment goal
○ Enrolled: Input the number of participants to be enrolled in the study
• % of Enrollment Target Met: This is a calculation. No need to input anything in these cells.
Tracking Enrollment Sources:
• Month: Input the month.
• Recruitment Strategies: Input the recruitment strategies for the month.
○ Including what recruitment sources were utilized, staff efforts (if applicable), etc.
• Number of Initial Participants Pre-Screened: Input the number of participant pre-screened for the month.
• Number of Participants Screened: Input the total number of participant screened for the month.
• Number of Participants Enrolled: Input the total number of participant enrolled in the month.
Recruitment Strategy Tracker |  | Recruitment Activities Summary
|  |  | Actual # of Participants | Target # of Participants | % of Enrollment Target Met
PI: |  | Initial Participants Pre-Screened | 100
Study: |  | Participants Screened | 35
|  | Participants Enrolled | 16
Tracking Recruitment Strategies
Month | Recruitment Strategies |  | Number of Initial Participants Pre-Screened | Number of Participants Screened | Number of Participants Enrolled
2020-01-01 | Recruitment Efforts Start: Recruitment Materials hung up around campus and businesses Potential subjects from Registries |  | 15 | 10 | 5
2020-02-01 | Additional potential subjects contacted from prior studies Clinicaltrials.gov set up for study. Brochures are printed and placed in NM clinics. |  | 35 | 5 | 2
2020-03-01 | EDW list generated with 500 potential subjects and EDW mailing/calling initiated A newspaper Ad posted in the Redeye Study registered under ResearchMatch |  | 50 | 20 | 9
Note on D25: Calculation: sums the participants from all sources
Note on E25: Input the target number of participants. This will assist with comparing actual participants to the target to ensure the study is on track with recruitment.
Note on F25: Calculation: percent of recruitment goal met to date
Note on A31: Column A = Month Input the month.
Note on B31: Column B = Recruitment Strategies Input the recruitment strategies utilized each month.
Note on D31: Column D = Number of Initial Participants Pre-Screened Input the number of participants pre-screened for the month.
Note on E31: Column E = Number of Participants Screened Input the number of participants screened. Update this as participants are screened.
Note on F31: Column F = Number of Participants Enrolled Input the number of participants enrolled. Update this as participants are enrolled.

## Tracker
Recruitment Strategy Tracker |  | Recruitment Activities Summary
|  |  | Actual # of Participants | Target # of Participants | % of Enrollment Target Met
PI: |  | Initial Participants Pre-Screened | 0
Study: |  | Participants Screened | 0
|  | Participants Enrolled | 0
[6 empty] | Cumulative | Cumulative | Cumulative
Tracking Recruitment Strategies
Month | Recruitment Strategies |  | Number of Initial Participants Pre-Screened | Number of Participants Screened | Number of Participants Enrolled | Number of Participants Pre-Screened | Number of Participants Consented | Number of Participants Enrolled
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
Note on D2: Calculation - do not override
Note on E2: Input the target number of participants. This will assist with comparing actual participants to the target to ensure the study is on track with recruitment.
Note on F2: Calculation - do not override
Note on A8: Input the month.
Note on B8: Input the recruitment strategies utilized each month.
Note on D8: Input the number of participants pre-screened. Update this as participants are pre-screened.
Note on E8: Input the number of participants screened. Update this as participants are screened.
Note on F8: Input the number of participants enrolled. Update this as participants are enrolled.